## Sprint 1 #1 (hidden)
(Let system admin can add 2022 new first level KPI in 2021 Dec.)
System admin add new first level KPI should select this KPI belongs to which year

## Sprint 2 #5 (hidden)
1.3 View KPI
Problem: Some KPI needs to be revised, the users may add or remove PIC or revise the start meeting time,,, But if we revise it on 1.2 page, the page 2.1 this KPI will be restarted and display the button Action. For solving this problem, please let admin revise some setting (KPI name/Creator/PIC/Start time/End time) but it doesn't effect to update in 2.1 page & it won't change "The last editor" & "The last edit time". In this page, all accounts (except Admin) can't revise. Edit buttons can be seen by Admin only.
| Level | KPI Name | Type | Creator | PIC | Mgmt. arrange | Start Meeting Display time | End Meeting Display time | The last editor | The last edit time
Let user revise. After updating, in 2.1 page, the KPI button still display button Update PDCA

## Sprint 2 #6 (hidden)
Create new page 1.5 (refer to 1.2)
1.5 Revise KPI
Let manager to revise some setting (KPI name/PIC/Start time/End time) but it doesn't effect to update in 2.1 page & it won't change "The last editor" & "The last edit time"
| Level | KPI Name | Type | PIC | Mgmt. arrange | Start Meeting Display time | End Meeting Display time | The last editor | The last edit time
Let user revise. After updating, in 2.1 page, the KPI button still display button Update PDCA

## Sprint 2 #7 (hidden)
4.1 Tracking progress
Create a new page to show the progress of submitted of all users.
But, if the login account belongs to FHO, then this page display all FHO users pending items. Let the managers know and to track his or her own deparment progress. | [5 empty] | But for admin, they need to know all users submitted progress. If the account is admin, then display all users progress.
Center | Dept. | Name | To do (Pending) | To do Total | % | Center | Dept. | Name | 2.1 To do | 2.1 Total | %
FHO | FHO | Swook | 0 | 10 | 100% | FHO | FHO | Swook | 0 | 10 | 100%
FHO | FHO | Yvonne | 2 | 4 | 50% | FHO | FHO | Yvonne | 2 | 4 | 50%
FHO | FHO | Ariel | 2 | 5 | 60% | FHO | FHO | Ariel | 2 | 5 | 60%
FHO | FHO | Nancy | 1 | 6 | 83.33% | FHO | FHO | Nancy | 1 | 6 | 83.33%
|  | Total | 5 | 25 | 80% | Operation Center |  | Coni | 1 | 11 | 90.91%
[6 empty] | Operation Center | Biz | Frank | 3 | 13 | 76.92%
PIC | # | KPI Objective |  |  |  | Operation Center | Planning | Morgan | 1 | 11 | 90.91%
Yvonne | 1 | 開發SAP相關專案推行上線 |  |  |  | Production Center | Prod. One | Liu | 2 | 12 | 83.33%
Yvonne | 2 | 建議箱系統順利上線 |  |  |  | Production Center | Prod. Two | LE VAN DAI | 2 | 12 | 83.33%
Ariel | 3 | 油墨房系統專案推行上線 |  |  |  | Production Center | Prod. Three | Kiem Ly | 2 | 12 | 83.33%
Ariel | 4 | 開發SAP相關專案推行上線 | [5 empty] | Total | 16 | 96 | 83.33%
Nancy | 5 | 協助廠區各部門釐清系統稽核疑難雜症
[6 empty] | PIC | # | KPI Objective
[6 empty] | Yvonne | 1 | 開發SAP相關專案推行上線
[6 empty] | Yvonne | 2 | 建議箱系統順利上線
[6 empty] | Ariel | 3 | 油墨房系統專案推行上線
[6 empty] | Ariel | 4 | 開發SAP相關專案推行上線
[6 empty] | Nancy | 5 | 協助廠區各部門釐清系統稽核疑難雜症
[6 empty] | Coni | 6 | ……
[6 empty] | Frank | 7 | ……
[6 empty] | Frank | 8 | ……
[6 empty] | Frank | 9 | ……
[6 empty] | Morgan | 10 | ……
[6 empty] | Liu | 11 | ……
[6 empty] | Liu | 12 | ……
[6 empty] | LE VAN DAI | 13 | ……
[6 empty] | LE VAN DAI | 14 | ……
[6 empty] | Kiem Ly | 15 | ……
[6 empty] | Kiem Ly | 16 | ……
How many KPIs haven't been submitted in 2.1 page
This user total have how many KPIs
Refers to 2.1 page

## Sprint 2 #8 (hidden)
Create new page 0.6 Mailing
| # | Report | Date | Frenquency | Sending Time | Recipient
| 1 | Tracking progress | 1, 7, 13, 16, 23, 28 | Monthly | 18:30
Daily
[7 empty] | Weekly | If admin select Weekly, the selections will be Mon. to Sat. | Mon | 1
[7 empty] | Monthly | Date | Tue | 2
[9 empty] | Wed | 3
[9 empty] | Thu | 4
[8 empty] | If admin select Monthly, then the selections will be which date, from 1st to 28th | Fri | 5
[9 empty] | Sat | 6
7
[8 empty] | Date |  | 8
9
10
11
[8 empty] | If admin select Daily, then this setting can be ignored. Date will be blank. |  | 12
13
[8 empty] | Date |  | 14
15
16
17
18
19
20
21
22
23
24
25
26
27
28

## Sprint 2 #24 (hidden)
Sheet name: Complete rate
Sheet name: Delay detail

## Sprint 2 #25 (hidden)
New data type: VP report
Swook will create a KPI (KPI name: Operation Focus for Next Three Months) , apply new data type VP report. Then in meeting page the UI look like below |  |  |  |  | 2.1 page
2.3 page
Operation Focus for Next Three Months
Operation Focus for Next Three Months
| # | Jan. | # | Feb |  | # | Focus point
| 1 | 2月要開始大量招工, SHC和GQT, 一定要朝開滿39條線的目標前進 | 1 | 2月要開始大量招工, SHC和GQT, 一定要朝開滿39條線的目標前進, 要全力提高報到人數與招募人數相符 |  | 1 | 2月要開始大量招工, SHC和GQT, 一定要朝開滿39條線的目標前進, 要全力提高報到人數與招募人數相符
| 2 | 要每天追蹤底部進度 | 2 | 3月開兩條成型線, 3月中開一條針車線
| 3 | GQT必須開始加強培訓多能工可生產新型體 | 3 | GQT必須開始加強培訓多能工可生產新型體
| 4 | 生產中心全力留人, 招人, 年後招到的新人不能隨便放任導致新人離開 | 4 | 生產中心全力留人, 招人, 年後招到的新人不能隨便放任導致新人離開
| 5 | NMD V3, Forum, ZX22重點型體 | 5 | NMD V3, Forum, ZX22重點型體, 全力趕NMD系列型體
| 6 | 2, 3月部份欠料事項, 重點追料, 廠商產能 | 6 | 2, 3月部份欠料事項, 重點追料, 廠商產能, 要每天追蹤底部進度
| 7 | FW22模具追蹤 | 7 | 量化進度
| 8 | 量化進度

## Sprint 2 #28 (hidden)
Move Submit button in 2.1 page

## Sprint 2 #31 (hidden)
1.1
Drop down list for selecting this KPI need to be updated PDCA or not, selection : Yes / No
If admin select Yes, then continue to select the Type & Start month & End month. This KPI will be displayed in the PIC's 2.1 page.
If admin select No, then admin doesn't need to select Type & Start month & End month.

## Sprint 3 #36
| Add one page 0.6 Job Title |  |  |  | Add new column in 0.2 Account
0.6 Job Title
0.2 Account
|  |  |  | ID | Username | Fullname | Password | Authority Group | Job Title | Email | Factory | Center | Dept. | Account Group | L1 Manager | Functional Leader
|  |  |  | 1 | C90512 | BJ Huang | ****** | Manager | Vice Director |  | SHC | 開發中心 | N/A | L0 | Erick Chong | N/A
| 職稱 | Job Title |  | 2 | C90417 | Vicky Lu | ****** | Manager | Manager |  | SHC | 開發中心 | N/A | L0 | BJ Huang | N/A
| 協理 | Director
| 特助一級 | Executive Specialist Level Ⅰ
| 副協理 | Vice Director
| 特助二級 | Executive Specialist Level Ⅱ
| 資深經理 | Senior Manager
| 高專一級 | Senior Specialist Level Ⅰ
| 經理 | Manager
| 高專二級 | Senior Specialist Level Ⅱ
| 副理 | Vice Manager
| 高專三級 | Senior Specialist Level III
| 襄理/廠長 | Assistant Manager / Factory Chief
| 高專四級 | Senior Specialist Level IV
| 主任 | Senior Section Chief
| 專員一級 | Specialist I
| 課長 | Section Chief
| 專員二級 | Specialist Ⅱ
Chinese version selections
English version selections

## New demand
# | Sprint | 提出日 Raised date | 提出者From | 模組Module | 項目Item | Demand | 需求內容Requirement | 需求原因Reason(Why you need this function) | PIC | 狀態Status | 完成日 Complete date | PM Memo | FHO Memo
1 | 1 | 2021-12-28 | Yvonne | 1.Maintain | 1.1 KPI Create | 建立一階KPI時可以選擇該KPI歸屬哪一個年度 | button Add window, When System admins add new first level KPI, they can select this KPI belongs to which year | Current design, system doesn't know this KPI belongs to which year | Lab team | Complete
2 | 1 | 2021-12-28 | Yvonne | 1.Maintain | 1.1 KPI Create | 頁面可以選擇查看哪一個年度 | Select display which year KPI | Easily view each year KPI structure | Lab team | Complete
3 | 1 | 2021-12-28 | Yvonne | 1.Maintain | 1.2 KPI 2nd & 3rd Create | 頁面可以選擇查看哪一個年度 | Select display which year KPI | Easily view each year KPI structure | Lab team | Complete
4 | 1 | 2021-12-28 | Yvonne | 1.Maintain | 1.3 View KPI | 頁面可以選擇查看哪一個年度 | Select display which year KPI | Easily view each year KPI structure | Lab team | Complete
5 | 2 | 2022-02-14 | Yvonne | 1.Maintain | 1.4 KPI Sequence | 新增欄位Creator 並允許Admin 修改部分資料並且不影響使用者更新 | Add new column (Creator), let Admin to revise some settings but it doesn't effect current user to update PDCA in 2.1 page - Lab team revise the authority of admin in 1.4 page, allow admin revise the last editor (creator) | CB admin help some manager to create the KPI, but admin can't revise the data in 1.2 page. The manage can't revise neither. | Lab team | Complete
6 | 2 | 2022-02-14 | Yvonne | 1.Maintain | New page | 讓主管可以自行修改某些設定，並且不影響2.1更新 | Create new page 1.5 Revise KPI, for managers to revise some settings, but keep updating | Yvonne has submitted in Jan. (button Action) But Swook revised one KPI content in Feb., In 2.1 page display Action again. | Lab team | Complete
7 | 2 | 2022-02-14 | Yvonne | 4.Report | New page | 追蹤進度 | Create new page 4.1 Tracking progress, for managers to track their own dept. submit progress. If the KPI PICs involve more than one departments, we need to display all PICs (not just my dept.) | now there's no page for us to know and track the progress | Lab team | Complete |  | revise the logic, check #19
8 | 2 | 2022-02-14 | Yvonne | 0.System | New page | 自動發送郵件附檔報表功能 | Create new page 0.6 Mailing to select which report and which period to auto send email | send email to remind some information to manager on the certain date & time | Lab team | In Progress | 2022-03-02 | revise the design, please check #8 page
9 | 2 | 2022-02-17 | Yvonne | 1.Maintain | 1.4 KPI Sequence | 新增一欄位設定報告順序，For 4.2 中心主管會議 頁面 | Add new column CHM, for setting the sequence of center head meeting report (for new page 4.2CHM) . If this cell is blank, it means this KPI isn't shown in page 4.2 CHM | There are many KPIs need to be reported in the meeting. We need to arrange the sequence for managers find KPIs easily. | Lab team | Complete
10 | 2 | 2022-02-17 | Yvonne | 4.Report | New page | 新增一頁給中心主管會議使用 | Create new page 4.2 CHM (refer to page 2.2), display the KPIs which are marked the sequence in page 1.4 column CHM and show it follow the sequence. | Current users are all A4 KPI user, but there are a few managers need to report in center head meeting. For us easily find the KPIs to view, we create a new page to display the KPIs. | Lab team | Complete
11 | 2 | 2022-02-17 | Yvonne | 1.Maintain | 1.1 KPI Create | 欄位改為必填 | button Add, all cells are necessary to fill in, if there's any is blank, then the user can't create successfully | User didn't select KPI type, but still create successfully (CB) | Lab team | Complete
12 | 2 | 2022-02-17 | Yvonne | 1.Maintain | 1.2 KPI 2nd & 3rd Create | 欄位改為必填 | button Add LL KPI, all cells are necessary to fill in, if there's any is blank, then the user can't create successfully | User didn't select KPI type, but still create successfully (CB) | Lab team | Complete
13 | 2 | 2022-02-17 | Yvonne | 2.Transaction | 2.1 My PDCA | 開放給使用者選擇Change System Date，因為當月執行的內容須等到下個月才能更新，主管反應不夠即時更新(會忘記) | Add Change System Date in 2.1, user can select the date. Default is today. They can only select from today to future. | Manager response he can't update this month D immediately. | Lab team | In Progress | 2022-02-24
14 | 2 | 2022-02-17 | Yvonne | 2.Transaction | 2.2 Meeting | 開放給管理員編輯目標, 實績等數據(因為有些主管們會輸入錯誤) | Allow Admin account can edit the numbers in 2.2 page | Some managers may typed the wrong numbers (and submitted). We need Admin help them revise. | Lab team | Terminate | 2022-02-24 | It need to check with lab team whether they start or not. If not, let's terminate this one, because 2.4 page can replace this function.
15 | 2 | 2022-02-24 | Yvonne | 2.Transaction | 2.1 My PDCA | 設定開始和結束時間後該項KPI在各頁面(在2.1 & 2.2 以及2.3頁面)出現的時間是一致的 | Original: user set the start meeting date & end meeting date only impact the 2.2 page, it display which month Revise to : If user create the KPI in Feb., set the start meeting date is Mar. 2022, end meeting date is Oct. 2022, then, display the button in 2.1 from Mar. 2022 to Nov. | user complain the start date doesn't relate to 2.1 page. She created in Feb. & set start date from Mar., she didn't need to update in Feb, but it displayed the button. | Lab team | In Progress |  | 3/30 tested, complete yet
16 | 2 | 2022-02-24 | Yvonne | 1.Maintain | 1.2 KPI 2nd & 3rd Create | 精簡名稱，去掉Meeting | Revise the name Original : Start meeting date Revise to : Start Month Original : End meeting date Revise to : End Month | abbreviate the name | Lab team | Complete
17 | 2 | 2022-02-24 | Yvonne | 1.Maintain | 1.2 KPI 2nd & 3rd Create | 選擇年月就好，不需要選擇日期 | Start date & End date, let user select year & month (no need to select the date) Default: Start date is the first date of month. End date is the last date of month. | Standarlize the option | Lab team | Complete
18 | 2 | 2022-02-24 | Yvonne | 1.Maintain | 1.2 KPI 2nd & 3rd Create | 不再選擇是否停止更新，只要在建立KPI時設定好開始和結束時間即可 | Remove [Terminate Update] this function. | let user select start & end date, and let them click on/off terminate update, the two options are conflict. | Lab team | Complete
19 | 2 | 2022-02-24 | Yvonne | 4.Report | 4.1 Tracking Progress | 修改4.1的Total KPI邏輯 revise the logic | 4.1 Total KPI : [Year] = this year AND in the updating period (from Start Meeting date to End Meeting Date) | Current logic it count the last year KPI in. It makes the total KPI number is incorrect. | Lab team | Complete | 2022-02-26 | 2/26 上線
20 | 2 | 2022-02-24 | Yvonne | 2.Transaction | 2.1 My PDCA | 取消Action按鈕，主管反應 希望在新增KPI的當月份也可以更新執行的內容 | Cancel Action button. Depends on the start date to display button Update PDCA | Manager response that he wanted to update PDCA after creating the KPI. | Lab team | Complete
21 | 2 | 2022-02-24 | Yvonne |  |  | 補充中文名稱以及修正英文名稱 | Revise name: 4.1 Tracking process -> Tracking progress Chinese: 1.4 KPI Sequence -> KPI 順序 1.5 KPI Revise -> 修改KPI 2.3 CHM -> 中心主管會議 4.1 Tracking progress -> 追蹤進度 | revise the name & translate to Chinese | Lab team | Complete |  | 4.1 Tracking progress
22 | 2 | 2022-02-24 | Yvonne | 1.Maintain | 1.5 Revise KPI | 讓各主管自行調整要報告的項目有哪些以及順序 | Change the column Sequence 2.2 to Sequence 2.3 | Let manager arrange report item & sequence | Lab team | Complete
23 | 2 | 2022-02-24 | Yvonne | 2.Transaction | 2.1 My PDCA | 允許使用者附檔是圖片檔 | Allow uesers upload file format is .png & .jpg | For center head meeting manager report | Lab team | Complete |  | Please refer to Suggestion box system, click the photo name, pop up in new tab of browser .
24 | 2 | 2022-02-25 | Yvonne | 4.Report | 4.1 Tracking Progress | 在追蹤的頁面新增導出excel檔案 按鈕 | Add a export excel button, above and botton part in two sheet | for email to remind user the progress | Lab team | Complete | 2022-02-26 | 2/26 上線
25 | 2 | 2022-02-25 | Yvonne | 2.Transaction | 2.1 My PDCA | 2.1 頁面的新格式(for 廠區主管在中心主管會議報告格式) | Add a new data type (VP report) in 1.2 page. New UI in 2.1 page | For VP report in center head meeting | Lab team | Terminate
26 | 2 | 2022-02-25 | Yvonne | 2.Transaction | 2.3 CHM | 2.3 頁面的新格式(for 廠區主管在中心主管會議報告格式) | Add a new data type (VP report) in 1.2 page. New UI in 2.3 page | For VP report in center head meeting | Lab team | Terminate
27 | 2 | 2022-02-28 | Yvonne | 2.Transaction | New page | 新增頁面給各使用者補過去資料以及修改過去資料 | Add new page for users to revise past PDCA. | VP request all users should complete their KPI PDCA content. | Lab team | Complete |  | 3/5 上線(2.4頁面)
28 | 2 | 2022-03-08 | Yvonne | 2.Transaction | 2.1 My PDCA | 將Submit按鈕改到2.1頁面 | Move Submit button to the 2.1 page, besides Update PDCA button. Click the Submit button (inside the window), that row still display in 2.1 page. After clicking the Submit button (beside update PDCA button in 2.1 page), then that row will be invisible. | Many user response that button Submit position isn't great for them operate, they mis-click easily. | Lab team | Complete | 2022-04-02
29 | 2 | 2022-03-08 | Yvonne | 1.Maintain | 1.2 KPI 2nd & 3rd Create | 限制共同PIC的權限，現行系統允許所有PIC編輯KPI設定內容，欲修改成僅限建立者可以編輯 | Limit all PICs (except the last editor) to revise KPI settings. Only the last editor (the same to creator) have the authority to edit. | Some PIC remove themselves from PIC column without permission of creator. | Lab team | Complete
30 | 2 | 2022-03-08 | Yvonne | 2.Transaction | 2.1 My PDCA | 使用者建立計劃的順序，現行系統: 先建的會變成最後一項，欲修改成順序按照使用者建立順序呈現 | the sequence of adding plan. The first plan I add, it should be #1. Current system display : the first plan I add, it will be the last plan | users said they usually add the most important plan as the first plan, but system display at the last. It effect user report plan sequence as well. | Lab team | Complete
30 | 2 | 2022-03-25 | Yvonne | 2.Transaction | 1.2 KPI 2nd & 3rd Create | 修改1.2邏輯, 所有使用者可以看到全部KPI，並且可以在任一項KPI底下展開 | Revise the logic. Display all levels & all PICs KPI. Include admin can see all KPIs. (For excample : Even though my manager doesn't create any KPI, I still can create my KPI.) | Even though the KPI isn't created by his or her manager, the user still can create under the KPI. Everyone can create under 1st level KPI. | Lab team | Complete | 2022-03-28
31 | 2 | 2022-03-30 | Yvonne | 1.Maintain | 1.1 KPI Create | 新增一個按鈕可用於新增下一階KPI, 給管理員用於新增一階KPI, 並且可以設定是否需要更新 | Add a new button (Add LL level KPI) in 1.1 page | for admin set up 1st level KPI | Lab team | Complete | 2022-04-02
32 | 2 | 2022-03-30 | Yvonne | 2.Transaction | 2.2 Meeting | 修改會議畫面邏輯，任何使用者點進2.2頁面，顯示所有同中心的KPI (沒有中心就是同部門的) | In 2.2 page, revise the logic of displaying item. Original: User clicks 2.2 it display his or her KPI only. Revise to : User clicks 2.2 display his or her center KPIs. | TSH center head Andy can't see the KPI of his subordinate's KPI (because it's not assigned by him). Andy need to select the filter Center to all first then select ADM again. | Lab team | Complete | 2022-04-02
33 | 2 | 2022-03-30 | Yvonne |  |  | 補充中文名稱以及修正英文名稱 | Revise item name: Original : Tracking process Revise to : Tracking progress Also need to revise the excel file name | revise the name & translate to Chinese | Lab team | Complete | 2022-04-02
34 | 2 | 2022-03-30 | Yvonne | 2.Transaction |  | 調整欄位順序 | 1.2 & 1.3 & 1.4 & 1.5 page Adjust the sequence of column. | Easily revise the setting. | Lab team | Complete | 2022-04-02
35 | 2 |  | Yvonne |  |  | 各廠管理員都可以任意選擇該廠的使用者 | Add Userpicker in admin account. For each factory admin, they only can select their own factory users. |  | Lab team | In Progress
36 | 3 | 2022-04-25 | Yvonne | 0.System | New page | 新增一頁定義職稱 | Add new page 0.6 Job Title, for admin set up job title | For select in 0.2 Job Title column | Lab team | New
37 | 3 | 2022-04-25 | Yvonne | 0.System | 0.2 Account | 在0.2頁面新增一欄，可以選擇個使用者的職稱 | Add new column Job Title in 0.2 Account page | For HR report needed | Lab team | New
38
39
40
41
42
43
44
45
46
Note on B1: Author: 每兩周為一個Sprint週期
Note on E1: Author: DHO規範
Note on F1: Author: 如需新增項目可以新增
Note on H1: Author: 必須清楚描述流程與邏輯步驟等，請新增分頁說明之。

## PIC (hidden)
| PIC | Status
Dept | Name | New
GHR | Tracy | In Progress
FHO | Yvonne | Test
FHO | Lab team | Wait IT update
Complete
On Hold
Terminate

## Item (hidden)
0.System
1.Maintain
2.Transaction
3.Kanban
4.Report | [5 empty] | New page
| 0.System | 1.Maintain | 2.Transaction | 3.Kanban | 4.Report | 0.1 OC
| 0.1 OC | 1.1 KPI Create | 2.1 My PDCA |  | 4.1 CHM | 0.2 Account
| 0.2 Account | 1.2 KPI 2nd & 3rd Create | 2.2 Meeting |  |  | 0.3 Updating Month
| 0.3 Updating Month | 1.3 View KPI |  |  |  | 0.4 Role
| 0.4 Role | 1.4 KPI Sequence |  |  |  | 0.5 Change Password
| 0.5 Change Password |  |  |  |  | 1.1 KPI Create
1.2 KPI 2nd & 3rd Create
1.3 View KPI
1.4 KPI Sequence
1.5 Revise KPI
2.1 My PDCA
2.2 Meeting
2.3 CHM
2.4 PDCA Content Revising
4.1 Tracking Progress